## Project Management Plan
Week | Task | Goals | Goals (Details)
2020-10-01 | Project Setup | Set up project repository and environment | Initialize Git repository, set up virtualenv
2020-10-08 | Basic Flask API | Develop basic Flask API structure | Create basic routes and configure app settings
2020-10-15 | ML Model Integration | Integrate pre-trained ML model into Flask API | Ensure model can load and process input
2020-10-22 | API Testing | Write and execute unit tests for API endpoints | Use pytest to automate testing
2020-10-29 | Dockerization | Containerize the application using Docker | Write Dockerfile and build Docker image
2020-11-05 | Azure Deployment | Deploy Flask API to Azure App Services | Use az webapp up for initial deployment
2020-11-12 | CI/CD Pipeline Setup | Set up CI/CD pipeline with Azure DevOps | Configure YAML pipeline and test deployments
2020-11-19 | API Enhancement | Add error handling and logging to the API | Improve API response structure and add logs
2020-11-26 | API Security | Implement basic authentication for the API | Use Flask-HTTPAuth or similar
2020-12-03 | Monitoring and Logging | Set up application monitoring and logging on Azure | Integrate with Azure Monitor or similar
2020-12-10 | Final Testing | Perform end-to-end testing of the deployed API | Validate with test cases and load testing
2020-12-17 | Project Wrap-Up | Document project, clean up repository, final review | Prepare README, finalize documentation